## Budget
LOW-COST HOUSING BUDGET - PHASE 1 (2 ROOMS)
Assumptions: Basic finish, self-help/community build, phased approach
Room size: 30m² each (60m² total for Phase 1)
Category | Item | Description | Unit | Quantity | Unit Cost (ZAR) | Total Cost (ZAR) | Notes | Timeline | Status
PRE-CONSTRUCTION | Property Transfer | Legal fees, transfer duty | Lump Sum | 1 | 15000 | 15000 | Andrew Thomas estimate | Apr-May 2026 | Pending
PRE-CONSTRUCTION | Building Plans | Basic plans for 2 rooms | Lump Sum | 1 | 10000 | 10000 | Local draughtsman | May-Jun 2026 | To quote
PRE-CONSTRUCTION | Municipal Fees | Plan submission/approval | Lump Sum | 1 | 3000 | 3000 | Soshanguve municipality | Jun-Jul 2026 | To confirm
PRE-CONSTRUCTION | Site Survey | Beacon/peg survey | Lump Sum | 1 | 4000 | 4000 | Property boundaries | 2026-05-01 | To quote
SITE PREP | Clearing | Clear vegetation | m2 | 200 | 30 | 6000 | Manual labour | 2026-11-01 | Estimate
SITE PREP | Excavation | Foundation trenches | m3 | 20 | 250 | 5000 | Manual/hire machine | 2026-11-01 | Estimate
FOUNDATIONS | Concrete | Foundation concrete | m3 | 10 | 2000 | 20000 | Mix on site | 2026-11-01 | Estimate
FOUNDATIONS | Blocks | Foundation blocks | Each | 800 | 12 | 9600 | Hollow concrete blocks | 2026-11-01 | Estimate
FOUNDATIONS | Damp proof | DPC membrane | m | 60 | 40 | 2400 |  | 2026-11-01 | Estimate
WALLS | Bricks/Blocks | Wall construction | Each | 4000 | 6 | 24000 | Hollow blocks cheaper | Nov-Dec 2026 | Estimate
WALLS | Cement/Sand | Mortar for blocks | m3 | 5 | 800 | 4000 |  | Nov-Dec 2026 | Estimate
ROOF | Timber | Roof trusses | m | 200 | 80 | 16000 | Pine timber | 2026-12-01 | Estimate
ROOF | Sheeting | Corrugated iron | m2 | 80 | 180 | 14400 | IBS sheeting | 2026-12-01 | Estimate
ROOF | Nails/Fittings | Roof fixings | Lump Sum | 1 | 2000 | 2000 |  | 2026-12-01 | Estimate
WINDOWS/DOORS | Windows | Basic aluminium | Each | 4 | 1500 | 6000 | 2 per room | 2026-12-01 | Estimate
WINDOWS/DOORS | Doors | Internal/external | Each | 6 | 2000 | 12000 | 2 rooms + entrance | 2026-12-01 | Estimate
WINDOWS/DOORS | Security | Burglar bars | Each | 4 | 800 | 3200 | For windows | 2026-12-01 | Estimate
FLOOR | Concrete | Floor slab | m2 | 60 | 200 | 12000 | 75mm thick | 2026-12-01 | Estimate
FLOOR | Screed | Floor finish | m2 | 60 | 50 | 3000 | Cement screed | 2026-12-01 | Estimate
PLASTER | Internal | Wall plaster | m2 | 240 | 60 | 14400 | Cement plaster | 2027-01-01 | Estimate
PLASTER | External | Wall plaster | m2 | 120 | 70 | 8400 | Weatherproof | 2027-01-01 | Estimate
PAINT | Paint | Internal/external | Litre | 80 | 120 | 9600 | 2 coats | 2027-01-01 | Estimate
ELECTRICAL | Wiring | Basic points | Room | 2 | 5000 | 10000 | Lights, plugs, DB | 2027-01-01 | Estimate
ELECTRICAL | Fittings | Lights, switches | Lump Sum | 1 | 3000 | 3000 |  | 2027-01-01 | Estimate
PLUMBING | Basic plumbing | Water connection | Room | 2 | 8000 | 16000 | If water available | 2027-01-01 | Estimate
PLUMBING | Sanitary | Toilet, basin | Room | 2 | 5000 | 10000 | Basic ceramic | 2027-01-01 | Estimate
EXTERNAL | Boundary | Basic fence | m | 50 | 200 | 10000 | Palissade fencing | 2027-01-01 | Estimate
EXTERNAL | Gate | Entrance gate | Set | 1 | 5000 | 5000 | Simple sliding | 2027-01-01 | Estimate
LABOUR | Skilled labour | Bricklayer, etc. | Days | 40 | 500 | 20000 | R500/day skilled | Nov-Jan | Estimate
LABOUR | General labour | Helpers | Days | 60 | 300 | 18000 | R300/day general | Nov-Jan | Estimate
CONTINGENCY | Unforeseen | 10% buffer | % | 10 |  | 27900 | 10% of R279,000 | Throughout | Reserve
PHASE 1 TOTAL (2 ROOMS) | [5 empty] | R 306,900
PHASE 2 (ADD 2 MORE ROOMS)
Category | Item | Description | Unit | Quantity | Unit Cost (ZAR) | Total Cost (ZAR) | Notes | Timeline | Status
Construction | Additional rooms | Same as Phase 1 | Room | 2 | 153450 | 306900 | 50% of Phase 1 cost | 2027 | Future
GRAND TOTAL (4 ROOMS) | [5 empty] | R 613,800 | Phased over 2 years
COST-SAVING STRATEGIES
Strategy | Potential Saving | Implementation | Risk
Owner labour | R 38,000 | Do clearing, painting, cleanup | Time commitment
Community build | R 20,000 | Organize community work days | Coordination needed
Second-hand materials | R 15,000 | Windows, doors, fittings | Quality variable
Phased services | R 16,000 | Delay plumbing to Phase 2 | Inconvenience
Basic finishes | R 10,000 | No tiles, basic fittings | Lower quality
TOTAL POTENTIAL SAVINGS | R 99,000
ADJUSTED PHASE 1 TOTAL | [5 empty] | R 207,900 | With all savings
open plan , 4X4 pluse and closed bath | 30000
20 x 15 meters - 300 sq meter

## Dashboard
SOSHANGUVE LOW-COST HOUSING PROJECT - DASHBOARD
ERF 14201, Soshanguve South Extension 13 Township
Owners: Moabelo//Mdledle & Mkhabela Partnership
Target: 2 rooms Phase 1 (Nov 2026), expand to 4 rooms Phase 2
PROJECT STATUS OVERVIEW
Phase | Status | Start Date | End Date | Progress | Owner | Notes
1. Property Transfer | In Progress | 2026-03-01 | 2026-05-01 | 70% | Andrew Thomas Attorneys | Weekly updates from Cassius Chauke
2. Design & Approvals | Not Started | 2026-05-01 | 2026-07-01 | 0% | Tlangelani/Inathi | Need architect & municipal submission
3. Procurement | Not Started | 2026-08-01 | 2026-10-01 | 0% | Tlangelani/Inathi | Contractor selection, material sourcing
4. Construction | Not Started | 2026-11-01 | 2027-04-01 | 0% | Contractor | 4-room build, 5-6 month timeline
5. Handover | Not Started | 2027-04-01 | 2027-05-01 | 0% | Tlangelani/Inathi | Occupancy certificate, final payments
FINANCIAL SUMMARY
Category | Budget (ZAR) | Actual (ZAR) | Variance | Status
Phase 1 Construction (2 rooms) | R 306,900 | R 0 | R 128,000 | Pending
Phase 2 Construction (2 rooms) | R 0 | R 0 | R 2,315,000 | Estimate
Contingency (10%) | R 30,690 | R 0 | R 231,500 | Reserve
Project Management | R 20,000 | R 0 | R 90,000 | Estimate
TOTAL PHASE 1 | R 357,590 | R 0 | R 2,764,500
KEY CONTACTS & PROFESSIONALS
Role | Name/Company | Contact | Email | Status | Notes
Conveyancing Attorney | Andrew Thomas Attorneys | 017 054 0005 | deeds@andrewthomas.co.za | Active | Cassius Chauke - handling transfer
Co-Owner | Inathi Mdledle |  | inathimdledle@gmail.com | Partner | 50% ownership
Architect/Draughtsman | TO BE HIRED |  |  | Pending | Need local Soshanguve/Gauteng based
Quantity Surveyor | TO BE HIRED |  |  | Pending | For detailed cost estimates
Structural Engineer | TO BE HIRED |  |  | Pending | If required by municipality
Contractor | TO BE HIRED |  |  | Pending | Get 3 quotes, check CIDB rating
SOUTH AFRICAN MATERIALS SOURCES
Material | Recommended Suppliers | Approx. Cost (ZAR) | Notes | Location Advantage
Bricks/Blocks | Corobrik, Brickor, Italtile | R 3.50-5.00 per brick | Clay face bricks common | Local Gauteng factories
Cement | PPC, Lafarge, AfriSam | R 120-150 per 50kg | PPC Surebuild common | Nationwide availability
Sand & Stone | Local quarry/supplier | R 300-500 per m³ | 19mm stone for concrete | Find Soshanguve local
Steel Reinforcement | Macsteel, SA Steel Mills | R 18-22 per kg | Y12, Y16 bars common | Gauteng based
Roofing (IBS) | Mabati, Safal Steel | R 250-350 per m² | Corrugated iron, color coated | Local Gauteng
Timber | Chamberlain, Timbercity | R 150-300 per m | Pine for roof structure | Builders Warehouse
Windows/Doors | Aluminium & Glass suppliers | R 2,500-4,000 per window | Aluminium frames standard | Local fabricators
Tiles | Italtile, Tile Africa, CTM | R 200-400 per m² | Ceramic floor tiles | Gauteng showrooms
Sanitaryware | Bathroom Bizarre, Builders | R 8,000-15,000 per set | Toilet, basin, tapware | Local suppliers
Electrical | Ellies, ARB, Voltex | R 15,000 per unit | DB, wiring, fittings | Wholesalers
Plumbing | Plumbware, Builders | R 20,000 per unit | Pipes, fittings, geyser | Local suppliers
CRITICAL PATH MILESTONES
Milestone | Target Date | Dependencies | Status | Owner | Notes
Transfer Registration | 2026-05-31 | Attorney completion | On Track | Attorney | Weekly updates
Site Visit & Assessment | 2026-05-15 | Transfer complete | Pending | Owners | With architect/contractor
Hire Architect | 2026-05-30 |  | Pending | Owners | Get 3 quotes
Building Plans Complete | 2026-06-30 | Architect hired | Pending | Architect | 4-6 week design period
Municipal Submission | 2026-07-15 | Plans ready | Pending | Owners | 4-8 week approval time
Plan Approval | 2026-09-15 | Municipal processing | Pending | Municipality | Follow up weekly
Contractor Selection | 2026-09-30 | Plans approved | Pending | Owners | Get 3 fixed-price quotes
Groundbreaking | 2026-11-01 | All above complete | Pending | Contractor | Official start
Foundation Complete | 2026-11-30 | Groundbreaking | Pending | Contractor | First inspection
Wall Plate Level | 2026-12-31 | Foundations | Pending | Contractor | Structure up
Roof Complete | 2027-01-31 | Walls up | Pending | Contractor | Watertight shell
Finishes Complete | 2027-03-31 | Roof on | Pending | Contractor | Internal work
Practical Completion | 2027-04-30 | All work done | Pending | Contractor | Snagging list
Occupancy Certificate | 2027-05-31 | Final inspections | Pending | Municipality | Move-in ready
RISK REGISTER
Risk | Probability | Impact | Mitigation | Owner | Status
Transfer delays | Medium | High | Weekly attorney follow-ups | Owners | Active
Plan approval delays | High | High | Submit early, follow up weekly | Owners | Pending
Cost overruns | High | High | Detailed QS, fixed-price contract | Owners | Pending
Contractor issues | Medium | High | Thorough vetting, staged payments | Owners | Pending
Material shortages | Medium | Medium | Order early, local suppliers | Contractor | Pending
Weather delays | Medium | Medium | Rainy season buffer | Contractor | Pending
Municipal service delays | High | Medium | Apply early, persistent follow-up | Owners | Pending
Funding shortfall | Low | High | Secure financing early, 10% contingency | Owners | Pending

## Checklist
IMMEDIATE NEXT ACTIONS (APRIL-MAY 2026)
Task | Description | Due Date | Owner | Status | Notes
Follow up with attorney | Weekly call/email to Cassius Chauke for transfer update | Every Friday | Tlangelani | Ongoing | Transfer is critical path
Schedule site visit | Visit ERF 14201 with Inathi to assess conditions | 2026-05-15 | Both | Pending | Take photos, measurements, assess access
Research local architects | Find 3 architects/draughtspeople in Soshanguve/Gauteng area | 2026-04-30 | Tlangelani | Pending | Check Google, local referrals, professional associations
Contact municipality | Call Soshanguve municipal planning department | 2026-04-25 | Inathi | Pending | Ask about zoning, submission process, timelines
Create shared folder | Google Drive folder for all project documents | 2026-04-20 | Tlangelani | Done | This spreadsheet is start
Share project plan | Send comprehensive plan to Inathi for review | 2026-04-20 | Tlangelani | Pending | Include budget, timeline, risks
Initial budget discussion | Discuss R2.7M estimate and funding options | 2026-04-25 | Both | Pending | 50/50 split? Loan needed?

## Suppliers
SOSHANGUVE AREA BUILDING MATERIAL SUPPLIERS
For Low-Cost Housing Project - ERF 14201, Soshanguve South Extension 13
CATEGORY | SUPPLIER | LOCATION | CONTACT | PRODUCTS | PRICE RANGE | DELIVERY TO SOSHANGUVE? | NOTES
BLOCKS/BRICKS | Local Block Yards (Soshanguve) | Soshanguve industrial areas | Ask locals | Hollow concrete blocks | R5-8 per block | Yes, local | Cheapest option, quality varies
BLOCKS/BRICKS | Corobrik Pretoria North | 209 Scheiding St, Pretoria North | 012 546 2000 | Clay bricks, blocks | R8-12 per brick | Likely yes | Better quality, more expensive
BLOCKS/BRICKS | Informal Block Makers | Soshanguve backyards | Community referral | Concrete blocks | R4-6 per block | Very local | Cheapest, inspect quality
CEMENT | PPC Pretoria North | 247 Scheiding St, Pretoria North | 012 842 4000 | Cement, aggregates | R100-120/50kg bag | Yes | Bulk discounts possible
CEMENT | Builders Warehouse | Multiple Pretoria locations | 012 543 1000 | Cement, building materials | R110-130/50kg bag | Area dependent | Convenient, slightly more
ROOFING | Safal Steel (Mabati) | 247 Scheiding St, Pretoria North | 012 842 4000 | Corrugated iron, IBS | R180-250/m² | Yes | Ask for 'second choice' discount
ROOFING | Local Metal Fabricators | Soshanguve workshops | Ask around | Cut-to-size sheeting | R150-200/m² | Very local | May be cheaper
ROOFING | Second-hand Suppliers | Pretoria scrapyards | Facebook Marketplace | Used roofing sheets | R80-150/m² | Possible | Inspect for rust/damage
TIMBER | Chamberlain Pretoria | 247 Scheiding St, Pretoria North | 012 842 4000 | Roof timber, structural | R80-150/m | Yes | Proper graded timber
TIMBER | Local Timber Yards | Pretoria North | Search Google Maps | Pine, structural wood | R70-120/m | Likely | Compare prices
WINDOWS/DOORS | Local Aluminium Workshops | Soshanguve/Pretoria North | Community referral | Custom windows/doors | R1,500-3,000/window | Yes | Custom sizes cheaper
WINDOWS/DOORS | Second-hand/Reclamation | Pretoria reclamation yards | Facebook Marketplace | Used windows/doors | R500-1,500 each | Possible | 50-70% savings
WINDOWS/DOORS | Builders Warehouse | Pretoria branches | 012 543 1000 | Standard windows/doors | R2,500-4,000 each | Area dependent | Convenient but pricey
HARDWARE/TOOLS | Mica Hardware Pretoria North | 399 Church St, Pretoria North | 012 546 8800 | Tools, fittings, hardware | Market prices | Likely | General hardware
HARDWARE/TOOLS | Local Hardware Shops | Soshanguve malls | Visit in person | Basic tools, fittings | Variable | Very local | Convenient for small items
SANITARY/TILES | Italtile | Pretoria showrooms | 012 998 2000 | Tiles, sanitaryware | Premium prices | Yes | Better for Phase 2
SANITARY/TILES | Builders Warehouse | Pretoria branches | 012 543 1000 | Basic sanitaryware | Budget range | Area dependent | Adequate for low-cost
SANITARY/TILES | Second-hand Sanitary | Reclamation yards | Facebook Marketplace | Used toilets, basins | 30-50% of new | Possible | Good condition available
ELECTRICAL | Voltex/ARB/Ellies | Pretoria branches | Search per branch | Wiring, DB, fittings | Market prices | Yes | Wholesale prices
ELECTRICAL | Builders Warehouse | Pretoria branches | 012 543 1000 | Basic electrical | Retail prices | Area dependent | Convenient
PLUMBING | Plumbware | Pretoria branches | 012 800 1000 | Pipes, fittings, geysers | Market prices | Yes | Specialized
PLUMBING | Builders Warehouse | Pretoria branches | 012 543 1000 | Basic plumbing | Retail prices | Area dependent | Adequate for basics
HOW TO FIND LOCAL SOSHANGUVE SUPPLIERS:
Method | Action | Who | Timeline | Expected Outcome
Drive Around | Tour Soshanguve industrial areas | Inathi (local) | 1 day | List of local suppliers with addresses
Ask Community | Talk to contractors, shop owners | Inathi | Ongoing | Personal referrals, best prices
Facebook Groups | Join 'Soshanguve Community' groups | Tlangelani | This week | Supplier recommendations
Google Maps | Search 'building materials Soshanguve' | Tlangelani | 1 hour | List of registered businesses
Phone Calls | Call Pretoria North suppliers | Tlangelani | 1 day | Delivery quotes, bulk prices
COST-SAVING TIPS FOR SOSHANGUVE:
Tip | Potential Saving | How To | Risk
Buy local blocks | 20-30% | Find backyard block makers | Quality control needed
Second-hand roofing | 40-60% | Facebook Marketplace, scrapyards | Rust/damage inspection
Cash payment discount | 5-10% | Pay cash not card | Security carrying cash
Collect yourself | R2,000-5,000 | Rent trailer/borrow bakkie | Transport logistics
Community bulk buy | 10-15% | Organize with neighbors | Coordination effort
Owner collection | Delivery fee saved | Pick up small items | Time consuming
Negotiate package | 5-10% | Buy all materials from one supplier | Less price shopping
IMMEDIATE SUPPLIER ACTIONS:
Action | Supplier | Contact Method | By When | Goal | Owner
Get block quotes | Local Soshanguve yards | Visit in person | 2026-04-30 | Best price for 4,000 blocks | Inathi
Cement bulk quote | PPC Pretoria North | Phone call | 2026-04-25 | Price for 100 bags + delivery | Tlangelani
Roofing options | Safal Steel + second-hand | Phone + Facebook | 2026-04-28 | Compare new vs used pricing | Tlangelani
Window quotes | Local aluminium workshops | Visit/phone | 2026-05-02 | Custom vs standard pricing | Inathi
Tool list | Mica/Builders | Online research | 2026-04-22 | List of essential tools needed | Tlangelani