## Summary
SOSHANGUVE PROPERTY BUILD PROJECT
Funding Strategy — Save-Then-Borrow ¦ ERF 14201, Soshanguve South Ext 13
KEY ASSUMPTIONS
Monthly — Tlangelani (R) | 1500
Monthly — Inathi (R) | 1500
Combined monthly saving (R) | 3000
Phase 1 total cost (R) | 210000
Paperwork budget (transfer, plans, fees) (R) | 30000
Construction loan target (R) | 165000
Contingency held separately (R) | 21000
PROJECT MILESTONES — BASE CASE (no lump sum)
Date | Month | Milestone
May 2026 | Month 1 | First R3,000 saved. Start attorney follow-up weekly cadence.
Mar 2027 | Month 11 | ~R33k saved. Paperwork funded: transfer, plans, municipal, survey.
Apr 2028 | Month 24 | ~R69k total saved, ~R39k balance post-paperwork. Loan-ready.
Mid 2028 | Month 26 | Apply for building loan (R150–180k) against titled property.
Late 2028 | Month 30 | Loan approved. BREAK GROUND. Phase 1a begins.
End 2029 | Month 44 | Phase 1 complete. Unit habitable and rentable.
SCENARIO COMPARISON — see 'Scenarios' tab
Scenario | Break Ground | Total Project Cost | Duration from Today
Base case (R3k/mo, no lump sum) | Late 2028 | ~R210k | 3 years
+ R20k lump sum from Inathi (June 2026) | Mid 2028 | ~R210k | 2.5 years
⚠ R20k lump sum is UNCONFIRMED — plan as if it does not arrive.

## Cash Flow (Base)
CASH FLOW — BASE CASE (R1,500/person/month ¦ No Lump Sum)
Blue = inputs you can change ¦ Black = formulas ¦ Green = cross-sheet links
Month | Date | Tlangelani (R) | Inathi (R) | Total In (R) | Spend (R) | Net (R) | Cumulative Balance (R)
1 | May 2026 | 1500 | 1500 | 3000 | 0 | 3000 | 3000
2 | Jun 2026 | 1500 | 1500 | 3000 | 0 | 3000 | 6000
3 | Jul 2026 | 1500 | 1500 | 3000 | 8000 | -5000 | 1000
4 | Aug 2026 | 1500 | 1500 | 3000 | 0 | 3000 | 4000
5 | Sep 2026 | 1500 | 1500 | 3000 | 7000 | -4000 | 0
6 | Oct 2026 | 1500 | 1500 | 3000 | 0 | 3000 | 3000
7 | Nov 2026 | 1500 | 1500 | 3000 | 9000 | -6000 | -3000
8 | Dec 2026 | 1500 | 1500 | 3000 | 0 | 3000 | 0
9 | Jan 2027 | 1500 | 1500 | 3000 | 4000 | -1000 | -1000
10 | Feb 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 2000
11 ★ Paperwork funded | Mar 2027 | 1500 | 1500 | 3000 | 2000 | 1000 | 3000
12 | Apr 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 6000
13 | May 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 9000
14 | Jun 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 12000
15 | Jul 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 15000
16 | Aug 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 18000
17 | Sep 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 21000
18 | Oct 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 24000
19 | Nov 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 27000
20 | Dec 2027 | 1500 | 1500 | 3000 | 0 | 3000 | 30000
21 | Jan 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 33000
22 | Feb 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 36000
23 | Mar 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 39000
24 ★ Loan-ready | Apr 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 42000
25 | May 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 45000
26 | Jun 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 48000
27 | Jul 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 51000
28 | Aug 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 54000
29 | Sep 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 57000
30 ★ TARGET: Break ground | Oct 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 60000
31 | Nov 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 63000
32 | Dec 2028 | 1500 | 1500 | 3000 | 0 | 3000 | 66000
33 | Jan 2029 | 1500 | 1500 | 3000 | 0 | 3000 | 69000
34 | Feb 2029 | 1500 | 1500 | 3000 | 0 | 3000 | 72000
35 | Mar 2029 | 1500 | 1500 | 3000 | 0 | 3000 | 75000
36 | Apr 2029 | 1500 | 1500 | 3000 | 0 | 3000 | 78000
TOTAL (36 months) |  | 54000 | 54000 | 108000 | 30000 |  | 78000
PAPERWORK SPEND SCHEDULE (Base Case)
Month 3 | Transfer costs (partial) | [5 empty] | 8000
Month 5 | Transfer costs (final) + Survey | [5 empty] | 7000
Month 7 | Architectural plans | [5 empty] | 9000
Month 9 | Municipal connection application | [5 empty] | 4000
Month 11 | Misc admin, approvals | [5 empty] | 2000

## Scenarios
SCENARIO COMPARISON
Toggle the R20k lump sum on/off to see its impact on the project timeline
BASE CASE |  | + R20,000 LUMP SUM (June 2026)
Monthly saving (combined) | R3,000 | Monthly saving (combined) | R3,000
One-off lump sum | R10000 | One-off lump sum | R20,000 (Inathi, unconfirmed)
Savings by Sep 2026 (5 mo) | R15,000 | Savings by Sep 2026 (5 mo) | R35,000 (incl. lump sum)
Paperwork fully funded by | March 2027 | Paperwork fully funded by | September 2026
Savings buffer after paperwork | ~R3,000 | Savings buffer after paperwork | ~R20,000
Loan-ready milestone | April 2028 | Loan-ready milestone | October 2027
Building loan applied | Mid 2028 | Building loan applied | Late 2027
TARGET: Break ground | Late 2028 | TARGET: Break ground | Early 2028
Phase 1 complete | End 2029 | Phase 1 complete | Mid 2029
Time saved vs base | — | Time saved vs base | ~6 months
Risk if lump sum doesn't arrive | N/A | Risk if lump sum doesn't arrive | Plan falls back to base case
⚠ IMPORTANT: Treat the R20k lump sum as a bonus, not a plan. The base case is the commitment. If R20k lands in June, redeploy it to paperwork immediately — do not save it for later use. That's what pulls the timeline forward.

## Milestones
PROJECT MILESTONES & ACTION TRACKER
Updated: April 2026 ¦ Owner: Tlangelani (finance/legal) & Inathi (site/local)
Target Date | Status | Milestone / Action | Owner
Apr–May 2026 | IN PROGRESS | Property transfer registers via Andrew Thomas Attorneys (Cassius Chauke) | Tlangelani
May 2026 | IN PROGRESS | Open joint savings account — first R3,000 deposited on pay day | Both
May 2026 | PENDING | Weekly attorney follow-up every Friday (email Cassius, log response) | Tlangelani
May 2026 | PENDING | Get 2–3 quotes for architectural plans from local draughtspersons | Inathi
Jun 2026 | PENDING | Confirm or deny R20k lump sum — update Scenarios tab accordingly | Inathi
Jul 2026 | PENDING | Transfer registered — obtain title deed, update Decision Log | Tlangelani
Aug 2026 | PENDING | Appoint draughtsperson, sign brief for architectural plans | Both
Nov 2026 | PENDING | Architectural plans submitted to municipality for approval | Tlangelani
Mar 2027 | PENDING | ★ MILESTONE: Paperwork fully funded (~R30k spent). Plans approved. | Tlangelani
Mar 2027 | PENDING | Begin building 'book' — get 3 contractor quotes for Phase 1a shell | Inathi
Apr 2027 | PENDING | Shift savings focus to building fund (R3k/mo to loan war chest) | Both
Apr 2028 | PENDING | ★ MILESTONE: Loan-ready — ~R39k balance, titled property, approved plans | Tlangelani
May 2028 | PENDING | Apply for building loan (R150–180k) — NHFC or commercial bank | Tlangelani
Sep 2028 | PENDING | ★ MILESTONE: Loan approved. Appoint contractor. Sign contract. | Both
Oct 2028 | PENDING | ★ BREAK GROUND — Phase 1a begins (watertight shell, R120k) | Inathi
Mar 2029 | PENDING | Phase 1a complete. Site inspection. Phase 1b begins (habitable). | Both
Jun 2029 | PENDING | Phase 1b complete. Electricity/water connected. Phase 1c begins. | Both
Sep 2029 | PENDING | ★ Phase 1 COMPLETE — unit rentable. First rental income. | Both

## Decision Log
DECISION LOG
Authoritative record of project decisions ¦ Update before each Sunday call
Date | Decision | Rationale | Impact / Notes
Apr 2026 | Adopted Minimum Viable Shell strategy — Phase 1 = watertight shell only | Both have full-time jobs; smaller scope = faster completion and less contractor risk | Phase 1 budget R210k; sub-phases 1a/1b/1c defined
Apr 2026 | Monthly contribution set at R1,500 each (R3,000 combined) | Reflects realistic disposable income; leaves headroom for personal obligations | Previous R8,500 figure was aspirational — revised down to lockable baseline
Apr 2026 | Save-then-borrow strategy adopted | At R3k/mo cash-only, Phase 1 takes 70 months. Borrow R150–180k against titled asset in 2028. | Saves ~3 years vs pure cash build. Requires titled property + approved plans for loan
Apr 2026 | R20k lump sum (Inathi) treated as UNCONFIRMED — not in base plan | Unconfirmed lump sums that enter base plan become crises when they don't arrive | If confirmed, deploy immediately to paperwork. See Scenarios tab for impact
Apr 2026 | Groundbreaking target: Oct 2028 (base case) | 18–24 months savings for paperwork + 6 months loan process | With R20k lump sum: could pull to Early 2028

## Weekly Check-In
WEEKLY CHECK-IN TEMPLATE
Sunday 19:00 call ¦ 30 minutes ¦ Copy a new block each week
WEEK OF:
Attorney status (transfer)
(Cassius contacted? Response received?)
Savings confirmed
(Both deposits made this month?)
Supplier / quote progress
(Any quotes received this week?)
Open issues / blockers
Actions before next call
Decisions needed